## Change Request Test Cases
Test Case ID | Change Request / Ticket No. | Module Affected | Feature / Function | Current Issue / Problem Description | Probable Error Message | Steps to Reproduce / Test Steps | Expected Result | Fix / Change Implemented | Test Environment | Tester | Test Date | Actual Result / Findings After Test | Test Status | Defect / Observation Reference | Remarks
TC-001 | TBD | Admissions (Admissions Queue + Admitted Patients list) | Admissions screen — search, status filter, Referring Department auto-fill | Three related gaps, all on the Admissions Queue table specifically (the top table listing patients dispositioned to admit but not yet assigned a ward/bed) — the separate Admitted Patients table below it is not affected by gap (2): (1) the Referring Department column is blank for several patients in the queue — it should auto-populate from the department the staff member checked in under, rather than relying on manual entry; (2) the Admissions Queue table has no search bar, making it hard to find a specific patient in a queue that can run 39+ entries deep — the Admitted Patients table below it already has a working "Search patient, admission #..." field, but that search does not reach the queue table above it; (3) there is no filter to toggle between "awaiting ward/bed assignment" (the Admissions Queue table) and "already admitted" (the separate admitted-patients table below it) — distinct from the existing Active/Discharged/All tabs, which track discharge status, not bed-assignment status, and belong to the Admitted Patients table only. | None observed. | 1. Open the Admissions screen. 2. Check the Admissions Queue table's Referring Department column for blanks. 3. Look for a patient-search control above the Admissions Queue table specifically (not the Admitted Patients table below it, which already has one). 4. Look for a filter distinguishing "awaiting bed" from "already admitted." | Referring Department should auto-fill from the staff member's checked-in department; the Admissions Queue table should get its own search bar (matching the one already on the Admitted Patients table below it) so staff can find a specific patient in the queue; a top-level filter should toggle between awaiting-assignment and already-admitted views. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live and re-verified on 2026-09-22 on the UAT environment (https://rcmsuat.craftsilicon.com): Referring Department blank on 5 of 7 rows in the Admissions Queue table; the Admissions Queue table itself has no search bar or filter; the Admitted Patients table below it does have a working search bar ("Search patient, admission #..."), a ward filter, a "Long stay only" checkbox, and Export CSV, but none of that reaches the Admissions Queue table above it. No awaiting-vs-admitted toggle present beyond the two tables already being visually separate. | FAIL | HMIS_Issues_Log.docx — Issue 1.
TC-002 | TBD | Wards & Beds screen, Active Admissions tab | Active Admissions list — search | Wards & Beds → Active Admissions is a second, separate path into admissions data alongside the main Admissions screen, and has the same missing-search gap — no way to search or filter the list, only scroll. | None observed. | 1. Open Wards & Beds. 2. Click the Active Admissions tab. 3. Look for a search or filter control on the list. | A search bar should let staff find a specific patient in this list, consistent with the fix expected on the main Admissions screen. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live — no search bar present on the Active Admissions list. | FAIL | HMIS_Issues_Log.docx — Issue 2. | Attempted re-verification on 2026-09-22 could not complete — the UAT environment (https://rcmsuat.craftsilicon.com) returned a 403 Forbidden on reload partway through this testing session, before the Wards & Beds → Active Admissions tab could be re-checked. Original confirmed finding above is unaffected.
TC-003 | TBD | Admit Patient modal (whole-form review) | Admission-time billing, clinical-team, safety, and referral fields | The Admit Patient modal is missing the following fields: Payer Type (Cash/SHA/Private Insurer); SHA Beneficiary/Member Number; SHA Pre-Authorization Number; Admitting/Consultant Doctor; Referring Facility/Referral Number; Next of Kin/emergency contact; and clinical safety history (known allergies, chronic illnesses/pre-existing conditions such as diabetes, hypertension, CKD, or asthma, seizure/fit history, and current home medications). These fields should be added to the admission flow. | None observed. | 1. Click "Admit Patient" for a queued patient. 2. Scroll through the full form. 3. Check for each field listed in the Problem Description. | All fields listed should be present and captured at admission, organized into logical steps (Bed & Billing → Clinical & Diagnosis → Safety & History → Next of Kin → Notes & Confirm). | A full 5-step Admit Patient redesign was built covering all fields above (Bed & Billing → Clinical & Diagnosis → Safety & History → Next of Kin → Notes & Confirm). Not yet built in the live app. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live — none of the listed fields exist on the current single-page modal. Redesigned 5-step prototype reviewed against the full field list. Open item: the original modal's "Admit for Observation" and "Don't Queue" checkboxes aren't visible in any of the 5 reviewed steps — worth confirming they weren't dropped. | FAIL | HMIS_Issues_Log.docx — Issue 3. Prototype: https://ozzaynetwork.github.io/Craft-care-pages/start-admission.html | Confirm the "Admit for Observation" / "Don't Queue" checkboxes' fate before this is built — flagged, not yet resolved.
TC-004 | TBD | Kardex → Add Order (Nursing Activity) modal, Enter Details step (Laboratory Details) | Laboratory order — Enter Details step, Lab Test search field | On the Enter Details step, field spacing is cramped, and the Lab Test search field (min 2 letters) returns no results — a nurse cannot search for or select a test. The Radiology Details step's equivalent field has the same defect. | None observed — the search silently returns no results. | 1. Open a patient's Kardex tab. 2. Click "+ Add Order", select order type "Laboratory". 3. On the Enter Details step, type 2+ letters into the Lab Test field. 4. Observe: no results appear, and the step's fields feel visually cramped. | Typing 2+ letters should show a filtered dropdown of matching configured lab tests (or radiology exams) that can be selected; field spacing should match the rest of the app. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Reproduced twice — once from a shared screenshot, once confirmed live on the production system. Not yet fixed. | FAIL | HMIS_Issues_Log.docx — Issue 4.
TC-005 | TBD | Kardex — right-hand "Current Medications" summary panel | Current Medications panel — unique drug listing | The panel pulls directly from the Kardex schedule, so it repeats each individual scheduled dose (e.g. "Panadol 500mg" shown five times) instead of listing each unique drug once. | None observed — not an error state, a data-source/aggregation issue. | 1. Open a patient's Kardex tab for a patient with a multi-dose medication order. 2. Look at the Current Medications card in the right-hand sidebar. 3. Count the entries for that drug. | Each unique drug the patient is currently on should appear once in the list, not once per scheduled dose. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live — a single drug's scheduled doses each produced their own line in the Current Medications card instead of being grouped into one entry. | FAIL | HMIS_Issues_Log.docx — Issue 5.
TC-006 | TBD | Patient record header (Kardex and other tabs) | Header — Consultant / Primary Diagnosis fields | The "Consultant" and "Primary Diagnosis" fields show blank ("—") even for long-admitted patients — observed on a patient 133 days into an ICU admission, and reconfirmed on a same-day admission. | None observed. | 1. Open any admitted patient's Kardex tab. 2. Look at the patient record header. 3. Check the Consultant and Primary Diagnosis fields. | Consultant and Primary Diagnosis should be populated — an Admitting/Consultant Doctor field needs to exist on the Admit Patient form to capture this at admission, or the fields should be editable/settable from the patient record if captured later. | Not yet implemented. Root cause: the Admit Patient modal has no field to capture an Admitting/Consultant Doctor or a Primary Diagnosis at the point of admission, so there is nothing to populate this header from. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed blank on a patient 133 days into an ICU admission, and reconfirmed on a same-day admission — not a data-entry lag issue, the field is simply never populated. | FAIL | HMIS_Issues_Log.docx — Issue 6.
TC-007 | TBD | Inpatient record — Lab Results, Radiology, and Procedure tabs | Dedicated history views per tab | These tabs show no history of their own — the Lab Results tab, for example, just displays a redirect note instead of the patient's actual lab history. | None observed. | 1. Open an admitted patient's record. 2. Click the Lab Results tab. 3. Observe only a redirect note, no actual result history. 4. Repeat for Radiology and Procedure tabs. | Each tab should show that patient's full history for its domain (lab results, radiology results, procedures) directly in place, even though the orders themselves are raised from the Kardex. | Not yet implemented. | Production — https://hcare.craftcollect.africa (UAT) | Kelvin Njuguna | 2026-09-17 | Confirmed live (UAT); not yet built. | FAIL | HMIS_Issues_Log.docx — Issue 7.
TC-008 | TBD | Medications tab | Stop / discontinue a current medication | There is currently no way to stop or discontinue a specific medication the patient is on from this tab. | N/A — feature does not exist yet. | 1. Open an admitted patient's Medications tab. 2. Attempt to find a control to stop/discontinue one of the listed current medications. | Each current medication should have a way to be stopped/discontinued, requiring a reason to be entered when stopping it. | Requested feature; not yet built. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live — no stop/discontinue control exists anywhere on the Medications tab. | FAIL | HMIS_Issues_Log.docx — Issue 8.
TC-009 | TBD | Documents tab | Upload / attach a document | The tab's own header text says "Consent forms, discharge summaries, and other patient documents," but it only auto-lists the system-generated Discharge Summary — there is no upload/attach button. | N/A — feature does not exist yet. | 1. Open an admitted patient's Documents tab. 2. Read the tab's own header text. 3. Look for an upload/attach control anywhere on the tab. | An upload/attach control should exist, consistent with what the tab's own header text already promises. | Not yet implemented. | Production — https://hcare.craftcollect.africa (UAT) | Kelvin Njuguna | 2026-09-17 | Confirmed live (UAT); not yet built. | FAIL | HMIS_Issues_Log.docx — Issue 9.
TC-010 | TBD | Kardex → Mark Done modal (e.g. "Mark done · dialysis") | Procedure completion capture — Personnel, Witness, Consent verification | (1) No field to record which staff member(s) actually performed/administered the procedure — the modal only has Date, Time, optional Clinical Notes, and an "Approved By" consent section (Not required / Patient / Next of Kin). (2) The "Approved By" consent section correctly lets either the Patient or Next of Kin consent, but has no separate Witness field alongside that choice. (3) Selecting Patient, or filling in Next-of-Kin details, immediately shows a "Verified" badge — with no actual verification step (signature, OTP, confirmation checkbox) behind it. | None observed — design/data-capture gap, not an error state. | 1. Open an admitted patient's Kardex tab with a pending procedure order. 2. Click "Mark Done" on that procedure. 3. Check for a field to record who performed it. 4. Select "Patient" or fill in Next of Kin under Approved By and observe the "Verified" badge appearing immediately. 5. Check for a separate Witness field. | The modal should capture an optional "Performed/Administered By" field (default to logged-in user, editable) plus optional additional staff, a separate Witness field alongside the Patient/Next-of-Kin consent choice, and should require an explicit verification step before showing consent as "Verified." | The prototype demonstrates a Personnel Involved section (Performed By + additional staff), covering part of this issue. A separate Witness field and consent-verification step remain to be scoped for the live build. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Live "Mark done · dialysis" modal — Next of Kin consent filled in; no Performed By or Witness field. Screenshot on file predates the Personnel Involved prototype update. | FAIL | HMIS_Issues_Log.docx — Issue 10. Prototype: https://ozzaynetwork.github.io/Craft-care-pages/approving-procedure.html
TC-011 | TBD | Kardex → Discharge Summary | Discharge disposition workflow + follow-up appointment | Today, Discharge Summary is a single flow with no disposition selector. Needed: five disposition types — Home/Routine, Referred Out, DAMA, Absconded, and Deceased — each with its own structured sub-form, plus a shared "Condition at Discharge" field. Additional requirement: after discharge, allow creating a next/follow-up appointment directly from the workflow — capturing appointment date, department, and reason for the visit. | N/A — feature does not exist yet. | 1. Open an admitted patient's Kardex tab. 2. Click "Discharge Summary". 3. Look for a disposition-type selector and a follow-up-appointment option. | A disposition selector should be present (Home/Routine, Referred Out, DAMA, Absconded, Deceased), each opening its own structured sub-form, with a shared Condition at Discharge field, and an option to create a follow-up appointment as part of the same workflow. | Design prototyped and verified — each of the five disposition types shows its own dedicated sub-form. Sample printable discharge summaries were also produced for each disposition. Not yet built in the live app. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live: only a single, disposition-less flow exists today. | FAIL | HMIS_Issues_Log.docx — Issue 11. Prototype: https://ozzaynetwork.github.io/Craft-care-pages/discharge-modal.html
TC-012 | TBD | Pharmacy — Dispense Prescription modal | Drug substitution on out-of-stock prescribed item | When dispensing a prescription, there is no way to substitute a drug for an equivalent one if the pharmacy does not have the prescribed item in stock — the only stock-related control is a "Pick Stock" dropdown for the prescribed drug itself. | None observed — for an out-of-stock item the drug line shows no way to select an alternate drug. | 1. Open a prescription in Pharmacy → Dispense Prescription where one line item is out of stock. 2. Attempt to substitute an equivalent/alternate drug for that line. | Pharmacy staff should be able to pick an equivalent/alternate drug (brand or generic) in place of an out-of-stock prescribed item, with the substitution recorded against the original prescription. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Confirmed live via the Dispense Prescription modal — no drug substitution option if the prescribed item is out of stock. | FAIL | HMIS_Issues_Log.docx — Issue 12.
TC-013 | TBD | Maternity → Open Labour Record (confirmed defect); Programs → Speciality Programs enrolment search — Diabetes, Cancer and Dialysis (confirmed, working correctly); Nutrition not yet tested | Patient search — real backend lookup | Live testing confirmed the Maternity search does not perform a real lookup: the Find action returns the same fixed patient (Hawa bulle) for any input, including a name that does not exist, and no new network request fires when Find is clicked. Diabetes, Cancer and Dialysis enrolment search were also tested live and found to search correctly — they do not share this defect. | None observed — search silently returns a fixed, unrelated result rather than erroring. | 1. Open Maternity → Open Labour Record. 2. Search for a patient name that does not exist. 3. Click Find and observe the result. 4. Repeat the equivalent search in Programs → Speciality Programs enrolment for Diabetes, Cancer, Dialysis, and Nutrition. | Maternity's search should perform a real backend lookup and return no result (or the correct patient) for a query that matches no one, consistent with how Diabetes/Cancer/Dialysis enrolment search already behaves. | Not yet implemented. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-18 | Confirmed live: Maternity's Open Labour Record patient search is not wired to a real search — it always shows the same fixed result regardless of query. Diabetes, Cancer and Dialysis enrolment search were tested live and work correctly. Nutrition enrolment search still to be tested. | FAIL | HMIS_Issues_Log.docx — Issue 13.
TC-014 | TBD | Maternity → Open Labour Record → Partograph tab → Add Entry | Partograph / Labour Care entry — WHO Labour Care Guide (2020) alignment | Supportive care is not captured at all — no fields for companion, pain relief, oral fluid, or maternal posture/position. Woman vitals capture Pulse, BP and Temperature, but not urine (protein/acetone). FHR is a single number field — no field for deceleration type (early/late/variable). Medication is limited to Oxytocin (drops/min) — no field for other medicines given or IV fluids during labour. Notes is a single free-text box instead of a structured Assessment and Plan. No alert-range indication on vital fields. Additional requirement: the Partograph should be reachable from two places — Maternity → Partograph, and the Inpatient Details tab — both backed by the same underlying labour record, with a way at admission to flag the patient is in active labour and attach/activate the labour record. | N/A — clinical data-capture gap, not an error state. | 1. Open a patient's Maternity → Open Labour Record. 2. Open the Partograph tab and click Add Entry. 3. Compare the fields present against the WHO Labour Care Guide (2020) paper form. | The entry modal should capture every field the WHO guide tracks per entry, with WHO safe ranges shown inline, and should be reachable and kept in sync from both Maternity and Inpatient Details. | Reviewed against the WHO Labour Care Guide (2020) and redesigned to close every gap above — FHR deceleration type, urine protein/acetone, other medicines/IV fluids, and a full Supportive Care section, each field showing its WHO safe range inline. Also redesigned as a dedicated "Partograph" tab within Inpatient Details (next to Triage), with dilation/FHR trend charts, an entries history table, a Labour Summary card, and a "Record Delivery" action. Prototyped and verified against the app's existing design system. Not yet built in the live app. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-17 | Current Partograph entry modal confirmed to capture FHR, liquor, moulding, descent, dilation, contractions, duration, oxytocin, BP, pulse and temperature only. Redesigned prototype reviewed and found to close every gap. | FAIL | HMIS_Issues_Log.docx — Issue 14. Prototype (Inpatient Partograph tab): https://ozzaynetwork.github.io/Craft-care-pages/inpatieont-patograph.html — Prototype (Partograph Entry modal): https://ozzaynetwork.github.io/Craft-care-pages/pathograph-recording.html
TC-015 | TBD | Inpatient Details → Cardex / Treatment Sheet | Separation of order instruction from order administration | Cardex and order administration were combined in a single screen — the same view let anyone add a new order and also act on it (Give/Held, Send Lab Request, Mark Done), with no separation between what was instructed and what was actually administered. | N/A — workflow/design gap, not an error state. | 1. Open an admitted patient's Kardex tab. 2. Observe that "+ Add Order" and the row-level Give/Held/Send Lab Request/Mark Done actions all live on the same screen. | Two separate tabs: Treatment Sheet, where the doctor/clinical officer writes instructions (the "+ Add Order" control lives here), and Cardex, where nurses continue to act on those instructions (Give/Held, Send Lab Request, Mark Done, View Details) as before. Each instruction on Treatment Sheet should carry an activity trail showing who instructed it, and — once acted on from Cardex — who logged it, who requested it (for lab orders), and who it was submitted to, each with a timestamp. Medication courses spanning more than a day should show a rollup on Treatment Sheet: day X of Y, doses given so far, and percentage complete. Tab order across the record: Triage, Partograph, Treatment Sheet, Cardex, Notes, Medications, Lab Results, Radiology, Billing, Documents, History, with "Kardex" relabelled "Cardex" throughout to match local terminology. | Treatment Sheet prototyped and cross-linked with the rest of the inpatient record (Triage, Partograph, Cardex). Removing Cardex's own "+ Add Order" control is the remaining step to complete the separation in the live build. | Production — https://hcare.craftcollect.africa | Kelvin Njuguna | 2026-09-18 | Confirmed live that Add Order and every row-level administration action sit on one screen. Redesigned Treatment Sheet prototype reviewed — multi-day progress rollup and per-order activity trail both confirmed present and working as designed. | FAIL | HMIS_Issues_Log.docx — Issue 15. Prototype: https://ozzaynetwork.github.io/Craft-care-pages/treatment-sheet.html

## Template Guidance
Field | Description
Test Case ID | Unique identifier, e.g. TC-001.
Change Request / Ticket No. | Reference number for the change being tested, e.g. CR-2026-001.
Module Affected | Specific module/system area impacted.
Feature / Function | Specific function being tested.
Current Issue / Problem Description | What's wrong, who/what is affected, under what condition it occurs.
Probable Error Message | Exact error message, HTTP status, log message, or observed system error, where applicable.
Steps to Reproduce / Test Steps | Numbered steps to reproduce the issue and/or execute the test.
Expected Result | What should happen after the fix is applied.
Fix / Change Implemented | Brief technical or functional description of the implemented fix.
Test Environment | UAT, QA, Production, staging, etc.
Tester | Person who executed the test.
Test Date | Date the test was executed.
Actual Result / Findings After Test | What actually happened; include evidence/observations where relevant.
Test Status | PASS, FAIL, BLOCKED, or NOT TESTED.
Defect / Observation Reference | Related defect, incident, or follow-up ticket if applicable.
Remarks | Additional notes, dependencies, risks, or recommendations.